## Sheet1
Project_ID | Project_Name | Department | State | City | Site Code | Budget(Cr) | Actual_Cost(Cr) | Cost Variance(Cr) | Expense_Type | Month | Status
MEIL_P001 | Polavaram Canal | IRRIGATION | AP | Vijayawada | S01 | 120 | 118 | 2 | Civil | 2024-01-01 | Completed
MEIL_P002 | Kaleshwaram Pump | IRRIGATION | TS | Karimnagar | S02 | 200 | 215 | -15 | Electrical | 2024-01-01 | Delayed
MEIL_P003 | Uddanam Water | Water Supply | AP | Srikakulam | S03 | 85 | 80 | 5 | Pipeline | 2024-02-01 | Completed
MEIL_P004 | Zojila Tunnel | ROADS | JK | Sonamarg | S04 | 450 | 470 | -20 | Tunneling | 2024-02-01 | Delayed
MEIL_P005 | Gas Pipeline | Oil & Gas | GJ | Surat | S05 | 150 | 145 | 5 | Pipeline | 2024-03-01 | On Track
MEIL_P006 | Solar Canal | POWER | GJ | Vadodara | S06 | 60 | 55 | 5 | Solar | 2024-03-01 | Completed
MEIL_P007 | Thermal Plant | POWER | TN | Tuticorin | S07 | 510 | 520 | -10 | Mechanical | 2024-04-01 | Delayed
MEIL_P008 | Water Grid | Water Supply | TS | Hyderabad | S08 | 90 | 85 | 5 | Civil | 2024-04-01 | On Track
MEIL_P009 | Highway Package | ROADS | MP | Indore | S09 | 300 | 295 | 5 | Civil | 2024-05-01 | Completed
MEIL_P010 | Metro Utility | INFRA | KA | Bengaluru | S10 | 110 | 130 | -20 | Utility | 2024-05-01 | Delayed
MEIL_P011 | Bridge Work | ROADS | AP | Nellore | S11 | 75 | 72 | 3 | Civil | 2024-06-01 | Completed
MEIL_P012 | Pipeline Zone-1 | Oil & Gas | GJ | Ankleshwar | S12 | 140 | 140 | 0 | Pipeline | 2024-06-01 | On Track
MEIL_P013 | Pump House | IRRIGATION | TS | Warangal | S13 | 95 | 98 | -3 | Electrical | 2024-07-01 | Delayed
MEIL_P014 | STP Project | Water Supply | MH | Pune | S14 | 60 | 58 | 2 | Mechanical | 2024-07-01 | Completed
MEIL_P015 | Canal Lining | IRRIGATION | AP | Kurnool | S15 | 40 | 42 | -2 | Civil | 2024-08-01 | Delayed
MEIL_P016 | Substation | POWER | OD | Cuttack | S16 | 70 | 68 | 2 | Electrical | 2024-08-01 | Completed
MEIL_P017 | Road Widening | ROADS | UP | Lucknow | S17 | 130 | 125 | 5 | Civil | 2024-09-01 | Completed
MEIL_P018 | Gas Station | Oil & Gas | WB | Durgapur | S18 | 55 | 60 | -5 | Mechanical | 2024-09-01 | Delayed
MEIL_P019 | Water Intake | Water Supply | TS | Nizamabad | S19 | 48 | 45 | 3 | Civil | 2024-10-01 | Completed
MEIL_P020 | Pipeline Zone-2 | Oil & Gas | GJ | Surat | S05 | 150 | 145 | 5 | Pipeline | 2024-03-01 | On Track

## Sheet2
Row Labels | Sum of Budget(Cr) | Sum of Actual_Cost(Cr) | Sum of Cost Variance(Cr) | Row Labels | Sum of Budget(Cr) | Sum of Actual_Cost(Cr) | Sum of Cost Variance(Cr)
INFRA | 110 | 130 | -20 | AP | 320 | 312 | 8
IRRIGATION | 455 | 473 | -18 | GJ | 500 | 485 | 15
Oil & Gas | 495 | 490 | 5 | JK | 450 | 470 | -20
POWER | 640 | 643 | -3 | KA | 110 | 130 | -20
ROADS | 955 | 962 | -7 | MH | 60 | 58 | 2
Water Supply | 283 | 268 | 15 | MP | 300 | 295 | 5
Grand Total | 2938 | 2966 | -28 | OD | 70 | 68 | 2
|  |  |  | TN | 510 | 520 | -10
Row Labels | Sum of Budget(Cr) | Sum of Actual_Cost(Cr) | Sum of Cost Variance(Cr) | TS | 433 | 443 | -10
AP | 320 | 312 | 8 | UP | 130 | 125 | 5
GJ | 500 | 485 | 15 | WB | 55 | 60 | -5
JK | 450 | 470 | -20 | Grand Total | 2938 | 2966 | -28
KA | 110 | 130 | -20
MH | 60 | 58 | 2 | Row Labels | Sum of Budget(Cr) | Sum of Actual_Cost(Cr) | Sum of Cost Variance(Cr)
MP | 300 | 295 | 5 | Jan | 320 | 333 | -13
OD | 70 | 68 | 2 | Feb | 535 | 550 | -15
TN | 510 | 520 | -10 | Mar | 360 | 345 | 15
TS | 433 | 443 | -10 | Apr | 600 | 605 | -5
UP | 130 | 125 | 5 | May | 410 | 425 | -15
WB | 55 | 60 | -5 | Jun | 215 | 212 | 3
Grand Total | 2938 | 2966 | -28 | Jul | 155 | 156 | -1
|  |  |  | Aug | 110 | 110 | 0
|  |  |  | Sep | 185 | 185 | 0
|  |  |  | Oct | 48 | 45 | 3
| Column1 | Column2 |  | Grand Total | 2938 | 2966 | -28
| Total Budget | 2938
| Total Cost | 2966
| Total Cost Variance | -28