## Sheet1
Project ID | Project Name | Location | Planned | Actual Dates | Planned Progress | Actual Progress | Progress Gap | Delay Days | Project Status | Remarks
MEIL_P001 | Polavaram Canal | AP | 2024-01-01 | 2024-01-05 | 100 | 98 | 2 | 4 | Delayed | Minor delay
MEIL_P002 | Kaleshwaram Pump | TS | 2024-01-01 | 2024-01-20 | 80 | 65 | 15 | 19 | Delayed | Material delay
MEIL_P003 | Uddanam Water | AP | 2024-01-10 | 2024-01-10 | 90 | 90 | 0 | 0 | On Track | On time
MEIL_P004 | Zojila Tunnel | JK | 2024-02-01 | 2024-02-25 | 70 | 55 | 15 | 24 | Delayed | Weather issue
MEIL_P005 | Gas Pipeline | GJ | 2024-02-15 | 2024-02-15 | 85 | 85 | 0 | 0 | On Track | Completed
MEIL_P006 | Solar Canal | GJ | 2024-02-20 | 2024-02-18 | 100 | 100 | 0 | -2 | Completed | Early finish
MEIL_P007 | Thermal Plant | TN | 2024-03-01 | 2024-03-20 | 60 | 50 | 10 | 19 | Delayed | Vendor issue
MEIL_P008 | Water Grid | TS | 2024-03-05 |  | 40 | 35 | 5 |  | Delayed | Pending update
MEIL_P009 | Highway Package | MP | 2024-03-10 | 2024-03-12 | 75 | 73 | 2 | 2 | Delayed | Minor delay
MEIL_P010 | Metro Utility | KA | 2024-03-15 | 2024-03-30 | 50 | 40 | 10 | 15 | Delayed | Design change

## Sheet2
Row Labels | Average of Planned Progress | Average of Actual Progress | Average of Progress Gap
Gas Pipeline | 85 | 85 | 0
Highway Package | 75 | 73 | 2
Kaleshwaram Pump | 80 | 65 | 15
Metro Utility | 50 | 40 | 10
Polavaram Canal | 100 | 98 | 2
Solar Canal | 100 | 100 | 0
Thermal Plant | 60 | 50 | 10
Uddanam Water | 90 | 90 | 0
Water Grid | 40 | 35 | 5
Zojila Tunnel | 70 | 55 | 15
Grand Total | 75 | 69.1 | 5.9
Row Labels | Sum of Progress Gap | Sum of Delay Days |  | Row Labels | Sum of Delay Days
Gas Pipeline | 0 | 0 |  | Completed | -2
Highway Package | 2 | 2 |  | Delayed | 83
Kaleshwaram Pump | 15 | 19 |  | On Track | 0
Metro Utility | 10 | 15 |  | Grand Total | 81
Polavaram Canal | 2 | 4
Solar Canal | 0 | -2
Thermal Plant | 10 | 19
Uddanam Water | 0 | 0
Water Grid | 5
Zojila Tunnel | 15 | 24
Grand Total | 59 | 81